## Nasir
To-do lists |  | Completed by: |  | Nasir
|  | Date: | 2014-11-19
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Yes | Design for request from is ready | 2014-11-04 | H | Nasir |  | 6 |  | 2014-11-29
No | Develop the request form submission with purchase | 2014-11-07 | H | Nasir, Hanumant |  | 18 | 5 | 2014-11-29 | Completed, Testing Remaining
No | Email notifications to member, vet, support | 2014-11-07 | M | Nasir, Hanumant |  | 18 |  | 2014-11-29 | Woked on Mail templete
No | View Econsultation for Pet Owner and Vet | 2014-11-07 | M | Nasir |  | 6 |  | 2014-11-29
No | Edit Econsultation for Pet Owner and Vet | 2014-11-07 | M | Nasir |  | 6 |  | 2014-11-29 | Vet Portal required
No | Schedule e-consultation in vet portal | 2014-11-07 | H | Nasir |  | 8 |  | 2014-11-29 | Vet Portal required
No | Generate e-consultation summary in vet portal | 2014-11-07 | H | Nasir |  | 12 |  | 2014-11-29 | HTML design required
No | Unit Testing & Bug Fixing | 2014-11-07 | M | Nasir |  | 16 |  | 2014-11-29
No | Integrate Econsultation Flash component | 2014-11-07 | M | Nasir |  | 8 |  | 2014-11-29 | Flash Developer will update some script on Server
Done? | Activ4Pets Mobile App | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | Gallery - API | 2014-11-14 | M | Nasir |  | 8 |  | 2014-11-14
No | Pet Info Share - API | 2014-11-14 | M | Nasir |  | 6 |  | 2014-11-14
No | Unit Testing & Bug Fixing | 2014-11-14 | H | Nasir |  | 18 | 6 | 2014-11-14 | Modification and creating new API according to Mobile Developer
Done? | ADO - MCH | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Yes | Test New CCD File | 2014-11-12 | H | Nasir |  | 6 | 15 | 2014-11-12 | CCD Import is Complete, But some Section can not be Imported because of incomplete data provided by MCH.
No | MCH Support & Bug Fixing | 2014-11-02 | H | Nasir | x | 4 |  |  | Bug fixing in MCH Import Process. Till today no bug is reported.
Yes | CCD Import Automation | 2014-11-17 | H | Nasir | x | 8 | 9 | 2014-11-18 | Generate all scripts for CCD Import Automation.
No | CCD HL7 and ADO Sections Mapping for MCH | 2014-11-18 | H | Nasir | x | 6 | 5 | 2014-11-18 | Today Arijit is send modify CCD, Only remaining is Immunization Section Import. Today may be finish. Testing is remaining

## vivek
To-do lists |  | Completed by: | Rahul Chavhan
|  | Date: | 2014-11-19
Done? | Activ4Pets - HSBC | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | Activ4Pets Mobile App | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | notification page redesign | 2014-11-19 |  |  |  | 3 hours | 3 hours | 2014-11-19
Yes | image crop andriod app | 2014-11-19 |  |  |  | 3 hours | 3 hours | 2014-11-19
Yes | help for abhishek sir image croping | 2014-11-19 |  |  |  | 1 hours | 1 hours | 2014-11-19
Yes | flow recheak and few normal issue clear | 2014-11-19 |  |  |  | 1 hours | 1 hours | 2014-11-19
Done? | ADO Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | ADO Blog | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | ADO - MCH | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | ADO - PayerFusion/ WellAway | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | Authorize.Net | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | ACTIVDR Website | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes

## Prachi
| To-do lists |  | Completed by: | Prachi
|  |  | Date: | 2014-11-19
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | Testing of Gallery Album(Add,View,Delete,Edit) | 2014-11-18 | M |  |  | 3 hrs |  |  | Not uploaded on server to test.
No | Testing of My Plan/ Upgrade Feature | 2014-11-18 | M | [5 empty] | Waiting for dev comments when he will be done with the development.
Done? | Activ4Pets Mobile App | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Yes | Re-test the fixed issues(ID card,Edit pet,Insurance,Veterinarian, Contact) and new feature My Account on iphone | 2014-11-19 | H |  | × | 4 hrs | 4 hrs |  | Issues found on My account and on re-fixed features. Report has been sent to corressponding dev.

## Suyog
To-do lists |  | Completed by: | Suyog
|  | Date: | 19/11/2014
Done? | ADO Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | Make the script for Tracker and send to Eric | 2014-11-20 | H | Suyog | x | 00:30 Hrs |  |  | SQL Script is generated and Mail was send to Eric, Waiting for Reply
No | Working on Mobile ADO FR,COM,IN domain | 2014-11-20 | H | Suyog | x | 4 Hrs. | 4 Hrs. |  | Mobile tracker for FR ,COM is done. IN is remaining.
No | Work for SMO with yogita | 2014-11-20 | M | Yogita,Suyog | x | 2 Hrs. | 2 Hrs. |  | I work with her to solve Issue for SMO for without centerID patient not able see asigned expert.
Yes | Make SQL script for Tracker COM, Tracker IN modifications | 2014-11-20 | H | Suyog | x | 1 Hrs. | 1 Hrs. |  | Sending to Eric. For push to live.

## Abhishek
To-do lists |  | Completed by: | Abhishek
|  | Date | 11/19/2014
Done? | Activ4Pets Mobile App | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | Bug Fixes | 2014-11-14 | H |  | x | 20 hrs | 1 hr |  | Adding changes to MyAccount, Edit Id Card
No | Updating Emergency Contact Pages | 2014-11-17 | M |  |  | 6 hrs |  |  | Updating screen flow for Edit Emergency Contact
No | Links | 2014-11-19 | L |  | x | 16 hrs | 7 hrs |  | Completed design implmentation & functionality for Links
No | Adding remainig features | 2014-11-21 | H |  |  | 20 hrs |  |  | Addding fetch for cover pet image. It requires update from Nasir API.

## Nutan
To-do lists |  | Completed by: | Nutan
|  | Date: | 2014-11-19
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | Gallery - Album | 2014-11-19 | H |  |  | 40 hrs
No | Edit Album gallery | 2014-11-18 |  | Nutan | x | 8 |  |  | WIP : Update in database is remaining.
Yes | Design Integration For Add Album Gallery, view Album Gallery, List Album Photo (individual Photo delete) | 2014-11-19 |  | Nutan | x | 7

## Yogita
To-do lists |  | Completed by: | Yogita
|  | Date: | 2014-11-18
Done? | Activ4Pets - HSBC | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | Activ4Pets Mobile App | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | ADO Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Yes | 1 . When patient with CenterID send SMO request | 2014-11-18 | H |  | x | Max 12 hrs | 7hrs | 2014-11-18 | COnfirmation Mail Received : 18.11.2014 (Evening) SMO modification on demofr according to given test cases 1 . When patient with CenterID send SMO request -- It is visible to all Medical directors with same CenterID and without CenterID only (Done) -- For the moment it is not visible to Medical Director with different CenterID(Done) Once medical director create committee ,Then It is visible to (Done) -- Medical directors with Different CenterID also ,If he is in committee .
Yes | 2 . When patient without CenterID send SMO request | 2014-11-19 | H |  | x |  | 8hrs | 2014-11-19 | 2 . When patient without CenterID send SMO request -- it is visible to all Medical directors without CenterID only(Done) -- For the moment it is not visible to Medical Director with CenterID(Done) Once medical director create committee ,Then It is visible to -- Medical directors with CenterID also ,If he is in committee .(Done) Note : I have tested this on demofr (IOS) but still I want Eirc to test it once from his side
Done? | ADO Blog | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | ADO - MCH | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | ADO - PayerFusion/ WellAway | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | Authorize.Net | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | ACTIVDR Website | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes

## Hanumant
To-do lists |  | Completed by: | Hanumant
|  | Date: | 2014-11-19
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Yes |  | 2014-11-19 | H |  |  | 4hrs | 4hrs |  | Econsultation Vallidation for Setup page ,confirmation page
No | chnages according to veterinarian expert in code | 2014-11-19 | H |  |  | 5 |  |  | changes for veterinarian expert for to assin vet to pet, | Email for vet is pending
Email change is pending for vet expert
Done? | Activ4Pets Mobile App | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | Re-test the fixed issues(ID card,Edit pet,Insurance,Veterinarian, Contact,EC,Health history) | 2014-11-18 | M |  | × | 4 hrs |  |  | No device is available to test.
on iphone

## Manik
To-do lists |  | Completed by: |  | Manik
|  | Date: | 2014-11-19
Done? | ADOP-Server/Network | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | All User Machine and switch side crimping or cable check | 2014-11-19 | M | Manik |  | 7 |  | 2014-11-26 | Because user facing discunnection Problem
No | Switch Rack cable Proper Tagging | 2014-11-19 | M | Manik |  | 7 |  | 2014-11-26 | Because user facing discunnection Problem
Yes | Resolve Mr Pratik sir Machine Visul studio 1912 error and Mouse replace | 2014-11-19 | M | Manik | X | 2 Hours |  | 2014-11-19
No | Verified User Pc software and Remove unwanted software. | 2014-11-19 | M | Manik |  | 7 |  | 2014-11-26
Yes | Test machine not working /functioning proper . | 2014-11-19 | M | Manik | X | 2 Hours |  | 2014-11-19
Yes | Machine No 13 Near Vivek connecting to Network | 2014-11-19 | H | Manik | X | 1 |  | 2014-11-19
No | Update antivirus software on all Machine. | 2014-11-19 | M | Manik |  | 3 |  | 2014-11-21

## Baban
To-do lists |  | Completed by: | Nutan
|  | Date: | 2014-11-19
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | MyPlan |  | H | Baban | x | 10 Hourse | 3 Hourse |  | Did Unit Testing on Myplan Renew/change plan. Pedro has made some changes In MyPlan, So was Understanding the Code and functional logic. In the afternoon Yoshita said to work on SMO Request Emails because Pedro will work on MyPlan.
Yes | SMO Request Emails | 2014-11-19 | H | baban | x | 9 Hourse | 5 Hourse |  | Made Email templete for SMO Request Emails as follows > Send Email to Vet Director for SMO Request > Send Email to Support for SMO Request > Send Email to User for SMO Request > Send Email to User for Payment Pending > Send Email to Vet Expert after assigned Expert for SMO request > Send Email to User for SMO request in Process > Send Email to Vet Director for SMO response from Expert > Send Email to User for SMO report Ready All these Emails templates are ready. Kairee system need to call these emails on the request. I talked with There developer and she will call these emails.

## Sheet1
To-do lists |  | Completed by: | Rahul Chavhan
|  | Date: | 2014-11-19
Done? | Activ4Pets - HSBC | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | Flash animated logo for ADO | 2014-11-19 |  |  | x | 12 hrs | 5 hrs
No | Developer Support | 2014-11-19 |  |  | x | 3 hrs | 3 hrs | 2014-11-18 | I fixed owner portal Gallery design issue with Nutan
Done? | Activ4Pets Mobile App | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | ADO Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes