## Nasir
To-do lists |  | Completed by: |  | Nasir
|  | Date: | 2014-11-20
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Yes | Design for request from is ready | 2014-11-04 | H | Nasir |  | 6 |  | 2014-11-29
No | Develop the request form submission with purchase | 2014-11-07 | H | Nasir, Hanumant |  | 18 | 5 | 2014-11-29 | Completed, Testing Remaining
No | Email notifications to member, vet, support | 2014-11-07 | M | Nasir, Hanumant |  | 18 |  | 2014-11-29 | Woked on Mail templete
No | View Econsultation for Pet Owner and Vet | 2014-11-07 | M | Nasir |  | 6 |  | 2014-11-29
No | Edit Econsultation for Pet Owner and Vet | 2014-11-07 | M | Nasir |  | 6 |  | 2014-11-29 | Vet Portal required
No | Schedule e-consultation in vet portal | 2014-11-07 | H | Nasir |  | 8 |  | 2014-11-29 | Vet Portal required
No | Generate e-consultation summary in vet portal | 2014-11-07 | H | Nasir |  | 12 |  | 2014-11-29 | HTML design required
No | Unit Testing & Bug Fixing | 2014-11-07 | M | Nasir |  | 16 |  | 2014-11-29
No | Integrate Econsultation Flash component | 2014-11-07 | M | Nasir |  | 8 |  | 2014-11-29 | Flash Developer will update some script on Server
Done? | Activ4Pets Mobile App | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | Gallery - API | 2014-11-14 | M | Nasir |  | 8 |  | 2014-11-14
No | Pet Info Share - API | 2014-11-14 | M | Nasir |  | 6 |  | 2014-11-14
No | Unit Testing & Bug Fixing | 2014-11-14 | H | Nasir | x | 18 | 10 | 2014-11-14 | Modification and creating new API according to Mobile Developer
Done? | ADO - MCH | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Yes | Test New CCD File | 2014-11-12 | H | Nasir |  | 6 | 15 | 2014-11-12 | CCD Import is Complete, But some Section can not be Imported because of incomplete data provided by MCH.
No | MCH Support & Bug Fixing | 2014-11-02 | H | Nasir | x | 4 |  |  | Bug fixing in MCH Import Process. Till today no bug is reported.
Yes | CCD Import Automation | 2014-11-17 | H | Nasir | x | 8 | 9 | 2014-11-18 | Generate all scripts for CCD Import Automation.
Yes | CCD HL7 and ADO Sections Mapping for MCH | 2014-11-18 | H | Nasir | x | 6 | 9 | 2014-11-18 | I push changes to Qacom.

## vivek
To-do lists |  | Completed by: | vivek karankal
|  | Date: | 2014-11-20
Done? | Activ4Pets - HSBC | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | Activ4Pets Mobile App | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | Service Page Design Start | 2014-11-20 |  |  |  | 16 hours |  | 2014-11-21 | econsoltation page design has been complet
Yes | Help for abhishek sir image crop | 2014-11-20 |  |  |  | 1 hours | 1 hours
Done? | ADO Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | ADO Blog | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | ADO - MCH | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | ADO - PayerFusion/ WellAway | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | Authorize.Net | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Done? | ACTIVDR Website | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes

## Prachi
| To-do lists |  | Completed by: | Prachi
|  |  | Date: | 2014-11-20
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Yes | Testing of Gallery Album(Add,View,Delete,Edit) on all browser | 2014-11-20 | M |  | x | 2 hrs |  |  | I was able to add,edit,view and delete album except on safari browser I was not able to add more than one photo.
Yes | Testing of E-consultation | 2014-11-20 | M |  | x | 1 hr |  |  | I was able to add e-consultation only but on email wrong time is showing.

## Suyog
To-do lists |  | Completed by: | Suyog
|  | Date: | 20/11/2014
Done? | ADO Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | Make the script for Tracker and send to Eric | 2014-11-20 | H | Suyog | x | 00:30 Hrs |  |  | SQL Script is generated and Mail was send to Eric, Waiting for Reply
Yes | Working on Mobile ADO FR,COM,IN domain | 2014-11-20 | H | Suyog | x | 5 Hrs. | 4 Hrs. |  | Tracker is working fine for COM,FR,IN
No | Testing SMO on DemoFR done by Yogita | 2014-11-20 | M | Yogita,Suyog | x | 2 Hrs. | 2 Hrs. |  | working fine on mobile Eric got issue with director login in SMO.
Yes | Thibault have issue with tracker working with him | 2014-11-20 | H | Suyog | x | 1 Hrs. | 1 Hrs. |  | He is working for missing records in TL_Tracker_Valuer . I will generate script to find missing records.

## Abhishek
To-do lists |  | Completed by: | Abhishek
|  | Date | 11/20/2014
Done? | Activ4Pets Mobile App | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | Bug Fixes | 2014-11-14 | H |  |  | 20 hrs
No | Updating Emergency Contact Pages | 2014-11-17 | M |  |  | 6 hrs |  |  | Updating screen flow for Edit Emergency Contact(Dependency on Nasir )
Yes | Links | 2014-11-19 | L |  |  | 16 hrs |  |  | Completed design implmentation & functionality for Links
No | Adding remainig features | 2014-11-21 | H |  |  | 20 hrs | 2 hrs |  | Addding fetch for cover pet image, pet image list. It requires update from Nasir API.
No | Changes after changes in API/ database fields | 2014-11-24 | H |  |  | 15 hrs | 6 hrs |  | Changes in Add Insurance, Add Medication, Add Contact, Add immunization, View My Account.(These task depends on how much time Nasir gives to me)

## Nutan
To-do lists |  | Completed by: | Nutan
|  | Date: | 2014-11-20
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Yes | Gallery - Album | 2014-11-19 | H |  |  | 40 hrs
Yes | Edit Album gallery | 2014-11-18 |  | Nutan | x | 8 | 10
Yes | Code upload on DINDE | 2014-11-20 |  | Nutan | x | 1 |  |  | Executed scripts for DB change
No | Notification for Econsultation in bell | 2014-11-20 |  | Nutan | x

## Yogita
Name: Yogita date : 11/20/2014
Done? | ADO Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Yes | Modification and testing for e-consultation on Demoinde | 2014-11-20 | H |  | x |  |  | 2014-11-20 | I was testing working of E-consulation on Demoinde but there was some issues . So,I fixed related issues and its working now Issue : When patient send E-consultation it was showing error. After solving above error again there was problem with chatting so i resolved that and its working fine now

## Hanumant
To-do lists |  | Completed by: | Hanumant
|  | Date: | 2014-11-20
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
Yes | Email for Vet Expert | 2014-11-19 | H | Hanumant |  | 4 hrs | 4 hrs
Yes | Add VetSpecility in Econsultation | 2014-11-18 | M | Hanumant | x | 4hrs | 4 hrs
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10
aaa

## Manik
To-do lists |  | Completed by: |  | Manik
|  | Date: | 2014-11-20
Done? | ADOP-Server/Network | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | All User Machine and switch side crimping or cable check | 2014-11-19 | M | Manik |  | 7 |  | 2014-11-26 | Because user facing discunnection Problem
No | Switch Rack cable Proper Tagging | 2014-11-19 | M | Manik |  | 7 |  | 2014-11-26 | Because user facing discunnection Problem
Yes | Internet Link down from Tata broadband | 2014-11-20 | H | Manik | X | 2 Hours |  | 2014-11-20 | Log Complete request to Tata -1167141120
No | Verified User Pc software and Remove unwanted software. | 2014-11-19 | M | Manik |  | 7 |  | 2014-11-26
Yes | Software Photoshop cc ( 3d module) related issue in Rahul machine | 2014-11-20 | M | Manik | X | 1 Hours |  | 2014-11-20 | For this 3D Module required Graphic card(GPU)
No | Update antivirus software on all Machine. | 2014-11-19 | M | Manik |  | 3 |  | 2014-11-21

## Rahul
To-do lists |  | Completed by: | Rahul
|  | Date: | 2014-11-20
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | 3D animated logo for ADO with globe | 2014-11-19 |  |  | x | 12 hrs | 8 hrs |  | Globe is ready but for 3D effect required graphics card. But it is not available on my system so I am looking another solution for 3D effect.
| activ4pets notification history page |  |  |  |  | 12 hrs

## Baban
To-do lists |  | Completed by: | baban
|  | Date: | 2014-11-20
Done? | Activ4Pets Platform | Due By | Priority | Assigned Team Member | Today | Estimated Duration | Actual Duration | Delivery Date | Notes
No | Share Pet Info |  | H | baban | x | 60 hrs | 6 hrs |  | Understanding the Use cases and the logic for Share pet info to social media, My contatcs and activ4pets community. Working on Database Schema design for Share pet info.
Yes | Promocode PETPLACE |  | H | baban | x | 2 | 2 |  | Worked on setting PETPLACE Promocode for signup. Genereted a link for PETPLACE promocode. Published last version on dinde.